## Sheet1
Area | Task/Responsibility | Cole | Cullen | Pratyusha | Robert | Samuel | Trey | Notes
| ADMIN: |  |  | S | R |  |  | Minor related
| Develop Agenda |  |  |  | R |  |  | Minor related
| Develop WBS and Resposibiliity Matrix |  |  |  | R |  |  | Minor related
| Leads Team Status Meetings |  |  | S | R | S |  | Minor related
| Status Reports / Email |  |  | S | R |  |  | Minor related
JAVA:
| Implementation of button to switch the project between English/Japanese text | [5 empty] | R | Minor related
| Generate data (temperature in-house per day) | R |  | C |  | I
| Generate data (temperature outside per day) | R |  | C |  | I | S
| Generate data (instances of doors opening/closing) | R |  | C |  | I
| Oversee connection of database to java code |  |  | R |  | R
| Randomize events | R |  |  |  |  | S
| Develop UI using JavaFX |  | R | C | S |  | I
| Administrative Page |  | R |  | S | S | I
| Data Page |  | R |  | S | S | I
| Creation of SQL Database |  |  | R |  | S
DATABASE:
| Brainstorm tables and table columns | I | I | R |  | S
| Create tables and columns | I | I | R |  | S
| Oversee connection of database to java code | I | I | R |  | S
DESIGN:
| Design 2D floor map |  | R | I |  | C
| Design On/Off Indicators for 2D floor map |  | R | I |  | C
| Desgin charts and graphs to visualize changes in home data |  | R | I |  | C
OTHER:
| Develop video presentation |  | R |  | S |  |  | Minor related
Legend
R | RESPONSIBLE - 'The Doer' - Responsible for action/implementation through their team - There must be at least one "R"
A | ACCOUNTABLE - 'The buck stops here' - Individual who is ultimately answerable for the action or decision - There can be only one "A"
S | SUPPORT - 'Helper' - Provides support and assistance to the "R"
C | CONSULTED - 'In the loop' - Subject Matter Expert to be consulted prior to action or decision
I | INFORMED - 'Keep in the picture' - Individuals who need to be informed after the action or decision